## Sheet1
No | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Risk Score | Status
1 | 3 | Ingredient Availability | Any disruptions in the food supply chain can affect menu availability. | Operational Risk | External factors such as weather transportation issues | Changes in supplier availability | Diversify suppliers to mitigate risks. | Operations Team | 5 | 8 | 40 | Ongoing
2 | 7 | Legal Issues | Security breach leading to legal issues. | Compliance and Legal Risk | Weaknesses in cybersecurity measures, lack of data encryption | Unauthorized access or data breach | Implement robust cybersecurity protocols. | IT Team | 3 | 9 | 27 | Ongoing
3 | 2 | Opportunity | The competitor loses market share and the demand for applications increases. | Market Risk | Competitor weaknesses, market trends favoring food delivery apps | Competitor's decline in market share | Capitalize on competitor's loss with targeted marketing campaigns. | Marketing Team | 8 | 7 | 56 | Ongoing
4 | 6 | Disruption | Technical bugs in the application cause delayed delivery to customers. | Implementation and Execution Risk | Software development flaws, compatibility issues with devices | Testing phase issues | Conduct thorough testing before app release. | IT Team | 4 | 8 | 32 | Ongoing
5 | 4 | Dependency | The project might face risks from dependencies on external APIs or data sources, which could change or become unavailable, affecting app functionality. | Technology and Infrastructure Risk | Unreliable API providers, changes in third-party data sources | PI or data source unavailability | Have backup plans or alternative data sources. | IT Team | 6 | 6 | 36 | Ongoing
6 | 5 | Legal | Breaches of contracts with restaurants, delivery drivers, or customers can lead to legal disputes. | Compliance and Legal Risk | Miscommunications, failure to meet contract terms | Failure to fulfill contractual obligations | Ensure clear and transparent contract agreements. | Legal Team | 4 | 8 | 32 | Ongoing
7 | 1 | Reputation | Positive user feedback and high ratings could enhance the company’s brand and reputation, leading to new opportunities in other markets or segments. | Strategic and Reputational Risk | Exceptional service, quality food offerings | User satisfaction and reviews | Engage with users, respond to feedback, and maintain quality standards. | Marketing Team | 9 | 7 | 63 | Ongoing
8 | 2 | Innovation | Emerging technologies could be leveraged to enhance the app’s features and performance, keeping it ahead of the competition. | Innovation and Technology Risk | Advancements in AI, IoT, and mobile technologies | Introduction of new technologies or features | Stay updated with industry trends and invest in research and development for new features. | IT Team | 8 | 7 | 56 | Ongoing